## Sheet2
Topic | (Multiple Items)
Row Labels | Count of Topic
Akash | 13
Dhyan | 15
Harshit | 15
Parshwa | 15
Grand Total | 58

## Sheet1
Date | Name | Topic
2023-07-11 | Harshit | Meeting to discuss about the project objective, design, and roles.
2023-07-11 | Dhyan | Meeting to discuss about the project objective, design, and roles.
2023-07-11 | Parshwa | Meeting to discuss about the project objective, design, and roles.
2023-07-11 | Akash | Meeting to discuss about the project objective, design, and roles.
2023-08-11 | Harshit | Shared ideas for the website's design and structure.
2023-08-11 | Dhyan | Shared ideas for the website's design and structure.
2023-08-11 | Parshwa | Shared ideas for the website's design and structure.
2023-08-11 | Akash | Shared ideas for the website's design and structure.
2023-09-11 | Harshit | Conducted research on similar websites for design inspiration.
2023-09-11 | Dhyan | Conducted research on similar websites for design inspiration.
2023-09-11 | Parshwa | Conducted research on similar websites for design inspiration.
2023-09-11 | Akash | Conducted research on similar websites for design inspiration.
2023-10-11 | Harshit | Create a GitHub Repo for project
2023-10-11 | Dhyan | -
2023-10-11 | Parshwa | Create a folder structure
2023-10-11 | Akash | -
2023-11-11 | Harshit | Create a wireframe for website
2023-11-11 | Dhyan | Create a wireframe for website
2023-11-11 | Parshwa | Create a wireframe for website
2023-11-11 | Akash | Create a wireframe for website
2023-12-11 | Harshit | -
2023-12-11 | Dhyan | -
2023-12-11 | Parshwa | -
2023-12-11 | Akash | -
11-13-23 | Harshit | Finalized the asset for the homepage
11-13-23 | Dhyan | Finalized the asset for the homepage
11-13-23 | Parshwa | Finalized the asset for the homepage
11-13-23 | Akash | Finalized the asset for the homepage
11-14-23 | Harshit | Worked on testimonial for the homepage of the website
11-14-23 | Dhyan | Worked on nav bar for the homepage of the website
11-14-23 | Parshwa | Worked on footer for the homepage of the website
11-14-23 | Akash | Worked on banner for the homepage of the website
11-15-23 | Harshit | -
11-15-23 | Dhyan | -
11-15-23 | Parshwa | Started working on website's logo
11-15-23 | Akash | -
11-16-23 | Harshit | -
11-16-23 | Dhyan | Worked on responsiveness of the nav bar
11-16-23 | Parshwa | -
11-16-23 | Akash | -
11-17-23 | Harshit | Started working on menu for the coffee products
11-17-23 | Dhyan | Completed the responsiveness of the nav bar
11-17-23 | Parshwa | Completed the website's logo
11-17-23 | Akash | Worked on Contact Us form
11-18-23 | Harshit | Worked on responsiveness of the menu
11-18-23 | Dhyan | -
11-18-23 | Parshwa | -
11-18-23 | Akash | -
11-19-23 | Harshit | Completed the menu
11-19-23 | Dhyan | Started working on About Us page
11-19-23 | Parshwa | Worked on responsiveness of the Contact Us page
11-19-23 | Akash | Worked on reponsiveness of the Contact Us page
11-20-23 | Harshit | -
11-20-23 | Dhyan | Worked on responsiveness of the About Us page
11-20-23 | Parshwa | -
11-20-23 | Akash | -
11-21-23 | Harshit | Started working on gallery page
11-21-23 | Dhyan | Started working on Blog page
11-21-23 | Parshwa | Started working on gallery page
11-21-23 | Akash | Started working on Blog page
11-22-23 | Harshit | -
11-22-23 | Dhyan | -
11-22-23 | Parshwa | -
11-22-23 | Akash | -
11-23-23 | Harshit | Completed the Gallery page
11-23-23 | Dhyan | Completed the Blog page
11-23-23 | Parshwa | Completed the Gallery page
11-23-23 | Akash | Completed the Blog page
11-24-23 | Harshit | -
11-24-23 | Dhyan | -
11-24-23 | Parshwa | -
11-24-23 | Akash | -
11-25-23 | Harshit | Started working on documentation for the project
11-25-23 | Dhyan | Started working on documentation for the project
11-25-23 | Parshwa | Started working on documentation for the project
11-25-23 | Akash | Started working on documentation for the project
11-26-23 | Harshit | Continued the documentation part of the project
11-26-23 | Dhyan | Continued the documentation part of the project
11-26-23 | Parshwa | Continued the documentation part of the project
11-26-23 | Akash | Continued the documentation part of the project
11-27-23 | Harshit | Worked on meeting the requirement of the project
11-27-23 | Dhyan | Worked on meeting the requirement of the project
11-27-23 | Parshwa | Worked on meeting the requirement of the project
11-27-23 | Akash | Worked on meeting the requirement of the project
11-28-23 | Harshit | Completed the documentation of the project
11-28-23 | Dhyan | Completed the documentation of the project
11-28-23 | Parshwa | Completed the documentation of the project
11-28-23 | Akash | Completed the documentation of the project
11-29-23 | Harshit | Completed the project
11-29-23 | Dhyan | Completed the project
11-29-23 | Parshwa | Completed the project
11-29-23 | Akash | Completed the project
11-30-23 | Harshit | -
11-30-23 | Dhyan | -
11-30-23 | Parshwa | -
11-30-23 | Akash | -